## Sheet1
Product Backlog
| Story ID | Sample Story | Status | Size | Sprint | Priority | Comments
| 1 | a single 1 to be worth 100 points | Done | 1 hour | 1 | 2
| 2 | roll of three 1’s to be worth 1000 points | Done | 1 hour | 1 | 3
| 3 | roll of four 1’s to be worth 2000 points | Done | 1 hour | 1 | 4
| 4 | roll of five 1’s to be worth 4000 points | Done | 1 hour | 1 | 5
| 5 | roll of six 1’s to be worth 8000 points | Done | 1 hour | 1 | 6
| 6 | roll of three 2’s to be worth 200 points | Done | 1 hour | 1 | 7
| 7 | roll of four 2’s to be worth 400 points | Done | 1 hour | 1 | 8
| 8 | roll of five 2’s to be worth 800 points | Done | 1 hour | 1 | 9
| 9 | roll of six 2’s to be worth 1000 points | Done | 1 hour | 1 | 10
| 10 | roll of three 3’s to be worth 300 points | Done | 1 hour | 1 | 11
| 11 | roll of four 3’s to be worth 600 points | Done | 1 hour | 1 | 12
| 12 | roll of five 3’s to be worth 1200 points | Done | 1 hour | 1 | 13
| 13 | roll of six 3’s to be worth 2400 points | Done | 1 hour | 1 | 14
| 14 | roll of three 4’s to be worth 400 points | Done | 1 hour | 1 | 15
| 15 | roll of four 4’s to be worth 800 points | Done | 1 hour | 1 | 16
| 16 | roll of five 4’s to be worth 1600 points | Done | 1 hour | 1 | 17
| 17 | roll of six 4’s to be worth 3200 points | Done | 1 hour | 1 | 18
| 18 | roll of a single 5 to be worth 50 points | Done | 1 hour | 1 | 19
| 19 | roll of three 5’s to be worth 500 points | Done | 1 hour | 1 | 20
| 20 | roll of four 5’s to be worth 1000 points | Done | 1 hour | 1 | 21
| 21 | roll of five 5’s to be worth 2000 points | Done | 1 hour | 1 | 22
| 22 | roll of six 5’s to be worth 4000 points | Done | 1 hour | 1 | 23
| 23 | roll of three 6’s to be worth 600 points | Done | 1 hour | 1 | 24
| 24 | roll of four 6’s to be worth 1200 points | Done | 1 hour | 1 | 25
| 25 | roll of five 6’s to be worth 2400 points | Done | 1 hour | 1 | 26
| 26 | roll of six 6’s to be worth 4800 points | Done | 1 hour | 1 | 27
| 27 | roll of 1, 2, 3, 4, 5, 6 to be worth 1000 points | Done | 1 hour | 1 | 28
| 28 | player to lose his or her points for the turn if his or her roll did not yield any points | Done | 2 hour | 2 | 29
| 29 | player to have a score of 1000 or more before he or she may decide to stop rolling during his or her turn | Done | 3 hour | 2 | 30
| 30 | player to continue rolling any dice from a previous roll that did not have any points attached to it | Done | 3 hour | 2 | 31
| 31 | player is able to roll all dice again if all dice have points attached to it | Done | 4 hour | 2 | 32
| 32 | Player is able to roll the dice | Done | 2 hour | 2 | 33
| 33 | Player able to hold current points | Done | 2 hour | 2 | 34
| 37 | New game allows for 2+ amount of players | Done | 1 hour | 2 | 38
| 38 | New game allows for adjustable game-winning point value | Done | 1 hour | 2 | 39
| 40 | Game to be played with six dice | Done | 1 hour | 2 | 1